## Task Tracker
Task ID | Task Name | Description | Phase | Contributors | Priority | Status | Start Date | End Date | Dependencies | Notes
1 | Topic | Explore topics based on research | Requirement |  | High | Completed | 2026-02-15 | 2026-02-25
2 | Scope | Define the scope | Requirement |  | High | Completed | 2026-02-25 | 2026-03-05
3 | Design | High level design | Design | All | High | Completed | 2026-03-01 | 2026-03-10
4 | Setup Environment | Install dependencies, setup repo, verify code runs | Setup |  | High | Pending
5 | Download INARA Dataset | Download full dataset and store locally | Data Collection |  | High | Pending |  |  |  | Required for all downstream tasks
6 | Create Dev Subset | Create 10K sample dataset for development | Data Collection |  | High | Pending |  |  | Task 2
7 | Run EDA on Full Data | Run and validate EDA notebooks on full dataset | EDA |  | Medium | Pending |  |  | Task 2
8 | Validate Synthetic Data Pipeline | Verify demo synthetic data generation logic | EDA |  | Low | Pending
9 | RandomForest Model Execution | Run notebook code for RandomForest baseline | Modeling |  | High | Pending |  |  | Task 3
10 | Prepare Data for CNN | Ensure npy files and preprocessing pipeline ready | Preprocessing |  | High | Pending |  |  | Task 3
11 | Fix 1D CNN Code | Debug and ensure CNN training works end-to-end | Modeling |  | High | Pending |  |  | Task 7
12 | Train CNN on Dev Data | Train CNN on 10K dataset | Modeling |  | High | Pending |  |  | Task 8
13 | Train CNN on Full Data | Scale training to full dataset | Modeling |  | Medium | Pending |  |  | Task 9
14 | Evaluate Models | Compare RandomForest vs CNN performance | Evaluation |  | High | Pending |  |  | Task 6,9
15 | Build Airflow DAG | Create DAG for pipeline automation | MLOps |  | High | Pending |  |  | Task 8
16 | Schedule Pipeline | Set up Airflow scheduler for automation | MLOps |  | Medium | Pending |  |  | Task 12
17 | End-to-End Pipeline | Integrate all steps into automated pipeline | MLOps |  | High | Pending |  |  | Task 12
18 | Deploy Model Locally | Prepare trained model for inference | Deployment |  | High | Pending |  |  | Task 10
19 | Build API Service | Create FastAPI service for predictions | Deployment |  | High | Pending |  |  | Task 15
20 | Test API | Test API with sample and batch inputs | Deployment |  | Medium | Pending |  |  | Task 16
| Create Demo UI (Optional) | Build Streamlit UI for demo | Deployment |  | Low | Pending |  |  | Task 16
| Final Demo Prep | Prepare demo flow and presentation | Presentation |  | High | Pending |  |  | Task 17
| Documentation | Prepare final report and documentation | Documentation |  | High | Pending |  |  | All tasks